marlo GO-TO-MARKET STRATEGY First 30 Providers · First 500 Parents · NYC Launch 2026

| OBJECTIVE Sign 30 vetted providers and acquire 500 paying parent subscribers in NYC within the first 90 days of launch. | THE PRINCIPLE Providers give Marlo credibility. Parents give Marlo revenue. You need both simultaneously — but providers come first by 30 days. |
| --- | --- |

# Launch Overview

| 30 TARGET PROVIDERS Brooklyn first | 500 TARGET PARENTS Paying subscribers | 90 DAY WINDOW Hard deadline | 3 NEIGHBORHOODS Park Slope / Cobble Hill / Carroll Gdns |
| --- | --- | --- | --- |

# The Two-Sided Launch Challenge

Marlo is a marketplace. Marketplaces have a chicken-and-egg problem: parents won’t subscribe if there are no providers, and providers won’t pay if there are no parents. The solution is sequencing — not doing both at once, but doing them in the right order.

| DAYS 1–30 Provider First Build the supply side manually. You call providers. You build their profiles. You sign them for free or reduced rate. Goal: 30 quality programs across 3 Brooklyn neighborhoods — before a single parent signs up. | DAYS 31–90 Parent Acquisition Once 30 programs are live, activate parent acquisition. Now the app has something to show. The first parent who opens Marlo sees real programs in their neighborhood. That’s the magic moment. |
| --- | --- |

# Part 1 — Signing the First 30 Providers

These are not cold sales calls. These are relationship conversations with local businesses who have a real problem Marlo solves: empty spots and manual enrollment chaos.

## Who Are the First 30?

| Category | Target Count | Why They Sign |
| --- | --- | --- |
| Soccer Leagues | 6 | Enrollment season pressure, parent database chaos, always seeking new families |
| Summer Camps | 6 | Urgency — camp season drives them to try anything that fills spots faster |
| Martial Arts Studios | 5 | High LTV per child, always recruiting, one-person operations with zero admin help |
| Dance & Performing Arts | 4 | Strong word-of-mouth culture, parent community is exactly Marlo’s audience |
| Music Lessons | 4 | Long retention (years per student), need steady new student pipeline |
| Coding & STEM Programs | 3 | Tech-forward, trust digital tools, early adopter energy |
| Visual Arts & Crafts | 2 | Underserved in existing directories, highly differentiated offering |

## The Provider Pitch

The pitch is never “pay for a listing.” The pitch is always one of two things:

| Pitch A — For Cautious Providers “We’re launching Marlo in Brooklyn — a platform that puts your program in front of parents actively searching right now. For our founding 30 providers, it’s completely free for the first 6 months. No card, no commitment. We build your profile, we drive the traffic. You just handle the enrollments.” Use for: Small studios, music teachers, solo operators | Pitch B — For Growth-Minded Providers “We’re signing founding providers at $49/month for the first year — locked in. After launch, this tier goes to $99. You get full profile, analytics, and priority placement. We’re starting in Park Slope and expanding borough-wide. You’re in the first wave or you’re not.” Use for: Established camps, competitive leagues, multi-location programs |
| --- | --- |

## How to Find and Contact Them

### Week 1–2: Research & List Building

- Search Google Maps for every soccer league, martial arts studio, dance school, music teacher, and camp in Park Slope, Cobble Hill, and Carroll Gardens

- Join and observe Park Slope Parents Facebook Group, Brooklyn Families, and local neighborhood Slack communities — note which programs get recommended organically

- Build a spreadsheet: name, category, contact email/phone, Instagram handle, website, notes on enrollment process

- Target: 80 potential providers to contact, expecting 30 to sign

### Week 3–4: Outreach

- Email first, follow up with DM on Instagram 3 days later if no response

- “Marlo is launching in Park Slope — [Business Name] should be in it”Subject line formula:

- Keep emails to 5 sentences maximum. Providers are busy. The shorter the ask, the higher the reply rate

- Offer a 20-minute Zoom to walk through the platform — screen share the Marlo screens, show the parent matching experience

- Close on the call. Ask for a decision, not a “think about it”

## The Founding Provider Offer

Make it easy to say yes. The founding provider deal is:

| Free FIRST 6 MONTHS No card required | $49 MONTHS 7–12 Locked founding rate | $99 POST-LAUNCH RATE What everyone else pays | 1hr PROFILE BUILD You do it for them |
| --- | --- | --- | --- |

The key detail: you build their profile for them. A parent-operator running a martial arts studio does not have time to upload photos and write descriptions. You show up with a draft profile, they approve it. That’s the service that gets you to 30 providers.

# Part 2 — Acquiring the First 500 Parents

The first 500 parents do not come from ads. They come from trust — which in Brooklyn means they come from other parents. Your acquisition channels are sequenced from highest trust to lowest.

## Channel 1: Direct Community Seeding (Days 31–45)

This is the highest-trust, highest-converting channel and it costs nothing but time.

- Identify the 10 most active parents in Park Slope Parents Facebook Group, local school parent associations, and neighborhood Slack communities

- Give them free Family Plan+ access in exchange for honest feedback and one post if they love it

- These 10 parents are your word-of-mouth engine. One genuine post in Park Slope Parents (≈ 38,000 members) can drive 200+ signups in 48 hours

- Script for them: “I’ve been testing a new app called Marlo — it found [child]’s Saturday soccer program in 30 seconds. Genuinely useful. Free trial at getmarlo.com”

### Target Communities for Seeding

- Park Slope Parents (Facebook — 38k members)

- Brooklyn Families Network (Facebook — 22k members)

- Cobble Hill Parents (NextDoor)

- Local school parent WhatsApp groups — PS 321, PS 107, PS 58

- Carroll Gardens Neighborhood Association

## Channel 2: Provider Co-Marketing (Days 35–60)

Your 30 providers have existing parent relationships. They are your distribution network.

- Give every founding provider 20 referral cards (physical and digital) to hand to their current families

- Ask each provider to post one Instagram story about being on Marlo — “We just joined Marlo, the easiest way to find programs like ours in Brooklyn”

- Place a Marlo QR code at the front desk of every brick-and-mortar provider

- Negotiate: providers who drive 10+ parent signups get an additional 3 months free on their plan

If each of 30 providers refers 8 parents on average, that’s 240 parents from this channel alone.

## Channel 3: Content & SEO (Days 1–ongoing)

Start publishing before launch. These articles rank over time and become passive acquisition.

- "Best Summer Camps in Park Slope 2026" — publish 60 days before camp registration season

- "After-School Programs in Brooklyn: The Complete 2026 Guide" — evergreen, high search volume

- "How to Find the Right Martial Arts Program for Your Kid in NYC"

- "Park Slope Soccer Leagues: Everything Brooklyn Parents Need to Know"

Each article links directly to the relevant Marlo search results. Parent clicks article, sees Marlo, signs up. This channel compounds every month.

## Channel 4: Paid Acquisition (Days 60–90)

Only activate paid after organic channels prove the conversion. Spending money to acquire parents who then churn is wasteful. Wait until you have a 30-day retention number you trust.

- Instagram and Facebook ads targeted at: Brooklyn parents, ages 28–42, with children, household income $80k+

- Creative: short video of the Sarah scenario — the before (chaos) and after (Marlo handled it)

- Target CPA: $15–25 per trial signup. At $14.99/month, payback period is 1–2 months

- Budget: $3,000–5,000 for the first paid campaign. Measure, optimize, scale only what works

# Week-by-Week Execution

| WEEKS 1–2 Research & Outreach Prep Build provider list of 80 targets. Draft outreach emails. Set up CRM tracking. | WEEKS 3–4 Provider Outreach Contact all 80 targets. Run 20-minute demo calls. Sign first 15 providers. | WEEKS 5–6 Profile Building Build all 30 provider profiles. Soft-launch the app internally. Seed 10 parent testers. | WEEKS 7–10 Parent Acquisition Community seeding live. Provider co-marketing active. Content publishing. Target: 300 parents. | WEEKS 11–13 Paid Acquisition + Optimize Launch first paid campaign. Hit 500 parent target. Gather reviews, testimonials, press. |
| --- | --- | --- | --- | --- |

# 90-Day Revenue Projection

| Revenue Stream | Month 1 | Month 3 | Month 6 |
| --- | --- | --- | --- |
| Parent Subscriptions (avg $14.99/mo) | 0 | $3,747 | $7,495 |
| Provider Growth Plans ($899/yr) | $0 | $8,990 | $26,970 |
| Provider Founding Rate ($49/mo) | $735 | $2,205 | $4,410 |
| Enrollment % Revenue (8–12%) | $0 | $2,500 | $8,000 |
| TOTAL MONTHLY REVENUE | — | ~$17,442 | ~$46,875 |

Month 6 run rate of ~$46,875/month = ~$562,500 annualized. This is the foundation Year 1 revenue is built on.

# How We Know It’s Working

| Metric | Week 4 Target | Week 8 Target | Week 13 Target |
| --- | --- | --- | --- |
| Providers signed | 15 | 28 | 30+ |
| Parent subscribers (paying) | 0 | 200 | 500 |
| Registrations through Marlo | 0 | 40 | 150 |
| Provider NPS (0–100) | N/A | 55+ | 65+ |
| Parent 30-day retention | N/A | 70%+ | 78%+ |
| Avg. sessions per parent / week | N/A | 2.5 | 3.5+ |

The first 30 providers and 500 parents are not just a launch metric. They are the proof of concept that funds everything after. Marlo’s got it.